## Sprint 1
Daily meeting sprint 1 (25/03/2019 - 31/03/2019)
Member | Tasks of previous week | Task for today | Individual implement | Date
NGUYEN VIET NGUYEN |  | List the users requirements |  | 25/03/2019
PHAM THANH THIEN |  | Create scrum documentation
HA THANH DUNG
TA XUAN HOANG SON |  | Create requirement specification
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN |  |  |  | 26/03/2019
PHAM THANH THIEN
TA XUAN HOANG SON
HA THANH DUNG
DUONG HOANG ANH TUAN |  | Design Wireframe
TRAN PHUOC DAT
NGUYEN VIET NGUYEN |  |  |  | 27/03/2019
PHAM THANH THIEN
TA XUAN HOANG SON
HA THANH DUNG
DUONG HOANG ANH TUAN
TRAN PHUOC DAT |  | Design Sitemap
NGUYEN VIET NGUYEN |  | Design Database |  | 28/03/2019
TA XUAN HOANG SON
PHAM THANH THIEN
HA THANH DUNG |  | Design Database
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN |  |  |  | 29/03/2019
TA XUAN HOANG SON
PHAM THANH THIEN
HA THANH DUNG |  | Input Sample Data
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN |  |  |  | 30/03/2019
TA XUAN HOANG SON
PHAM THANH THIEN
HA THANH DUNG |  | Design Website interface
DUONG HOANG ANH TUAN
TRAN PHUOC DAT

## Sprint 2
Daily meeting sprint 2 (01/04/2019 - 07/04/2019)
Member | Tasks of previous week | Task for today | Individual implement | Date
NGUYEN VIET NGUYEN | List the users requirements | Testing implemented functions of website |  | 2019-01-04
PHAM THANH THIEN | Create scrum documentation | Create scrum documentation
TA XUAN HOANG SON | Create requirement specification | Fix error of website
HA THANH DUNG
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN |  | Review Wirefram and Sitemap |  | 2019-02-04
PHAM THANH THIEN |  | Create scrum documentation
TA XUAN HOANG SON |  | Fix error of website
HA THANH DUNG |  | Login function
DUONG HOANG ANH TUAN | Design Wireframe
TRAN PHUOC DAT
NGUYEN VIET NGUYEN |  | Testing implemented functions of website |  | 2019-03-04
PHAM THANH THIEN |  | Create scrum documentation
TA XUAN HOANG SON
HA THANH DUNG
DUONG HOANG ANH TUAN |  | Create sample data for website
TRAN PHUOC DAT | Design Sitemap | Create sample data for website
NGUYEN VIET NGUYEN |  | Testing implemented functions of website |  | 2019-04-04
PHAM THANH THIEN |  | Create scrum documentation
TA XUAN HOANG SON
HA THANH DUNG |  | Upload function
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Design Database | Testing implemented functions of website |  | 2019-05-04
PHAM THANH THIEN |  | Create scrum documentation
TA XUAN HOANG SON |  | Fix error for website
HA THANH DUNG | Design Database | Send mail function
DUONG HOANG ANH TUAN
TRAN PHUOC DAT

## Sprint 3
Daily meeting sprint 3 (08/04/2019 - 14/04/2019)
Member | Tasks of previous week | Task for today | Individual implement | Date
NGUYEN VIET NGUYEN | Testing implemented functions of website | Testing implemented functions of website |  | 2019-08-04
PHAM THANH THIEN | Create scrum documentation | Design website interface
TA XUAN HOANG SON |  | Create bug list and fix bugs
HA THANH DUNG |  | Create interfaces for website
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Review Wirefram and Sitemap | Testing implemented functions of website |  | 2019-09-04
PHAM THANH THIEN | Create scrum documentation | Design Functionalities for marketing coordinator
TA XUAN HOANG SON
HA THANH DUNG | Login function | Create functionalities for marketing coordinator
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Testing implemented functions of website |  | 2019-10-04
PHAM THANH THIEN | Create scrum documentation | Design functionalities for University Marketing Manager
TA XUAN HOANG SON
HA THANH DUNG |  | Create functionalities for University Marketing Manager
DUONG HOANG ANH TUAN | Create sample data for website
TRAN PHUOC DAT | Create sample data for website
NGUYEN VIET NGUYEN | Testing implemented functions of website | Testing implemented functions of website |  | 2019-11-04
PHAM THANH THIEN | Create scrum documentation | Design functionalities for Guest
TA XUAN HOANG SON
HA THANH DUNG | Upload function | Create functionalities for Guest
DUONG HOANG ANH TUAN |  | Create scrum documentation
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Testing implemented functions of website |  | 2019-12-04
PHAM THANH THIEN | Create scrum documentation | Design Functionalities for Student
TA XUAN HOANG SON |  | Create bug list and fix bugs
HA THANH DUNG | Send mail function | Create Functionalities for Student
DUONG HOANG ANH TUAN
TRAN PHUOC DAT |  | Create scrum documentation

## Sprint 4
Daily meeting sprint 4 (15/04/2019 - 21/04/2019)
Member | Tasks of previous day | Task for today | Individual implement | Date
NGUYEN VIET NGUYEN | Testing implemented functions of website | Create download function, create scrum documentation |  | 15/4/2019
PHAM THANH THIEN | Design website interface | Testing implemented functions of website
TA XUAN HOANG SON | Create bug list and fix bugs
HA THANH DUNG | Create interfaces for website | Design download fucntion
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Testing implemented functions of website |  | 16/4/2019
PHAM THANH THIEN | Design Functionalities for marketing coordinator | Create scrum documentation, design date management feature
TA XUAN HOANG SON
HA THANH DUNG | Create functionalities for marketing coordinator | Create date management feature
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Design View Only interface, create scrum documentation |  | 17/4/2019
PHAM THANH THIEN | Design functionalities for University Marketing Manager | Testing implemented functions of website
TA XUAN HOANG SON
HA THANH DUNG | Create functionalities for University Marketing Manager | Create View Only interface
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Create Term and Condition, create scrum documentaion |  | 18/4/2019
PHAM THANH THIEN | Design functionalities for Guest | Testing implemented functions of website
TA XUAN HOANG SON
HA THANH DUNG | Create functionalities for Guest | Create Term and Condition interface
DUONG HOANG ANH TUAN | Create scrum documentation
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Testing implemented functions of website |  | 19/4/2019
PHAM THANH THIEN | Design Functionalities for Student | Create scrum documentation
TA XUAN HOANG SON | Create bug list and fix bugs
HA THANH DUNG | Create Functionalities for Student | Create Block upload feature
DUONG HOANG ANH TUAN
TRAN PHUOC DAT | Create scrum documentation
NGUYEN VIET NGUYEN |  | Testing implemented functions of website, create scrum documentation |  | 20/4/2019
PHAM THANH THIEN |  | Design student registration interface
TA XUAN HOANG SON
HA THANH DUNG |  | Create student registration function
DUONG HOANG ANH TUAN
TRAN PHUOC DAT

## Sprint 5
Daily meeting sprint 5 (22/04/2019 - 29/04/2019)
Member | Tasks of previous week | Task for today | Individual implement | Date
NGUYEN VIET NGUYEN | Create download function, create scrum documentation | Testing implemented functions of website, create srum documentation |  | 22/4/2019
PHAM THANH THIEN | Testing implemented functions of website | Design data encryption feature
TA XUAN HOANG SON |  | Design screencast documentation
HA THANH DUNG | Design download fucntion | Implement data encryption feature
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website | Implement notification system |  | 23/4/2019
PHAM THANH THIEN | Create scrum documentation, design date management feature | Design notification system
TA XUAN HOANG SON |  | Creat screencast video
HA THANH DUNG | Create date management feature | Testing implemented functions of website, create srum documentation
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Design View Only interface, create scrum documentation | Implement validation system |  | 24/4/2019
PHAM THANH THIEN | Testing implemented functions of website | Testing implemented functions of website, create srum documentation
TA XUAN HOANG SON |  | Create screencast documentation
HA THANH DUNG | Create View Only interface | Design validation system
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Create Term and Condition, create scrum documentaion | Testing implemented functions of website, create srum documentation |  | 25/4/2019
PHAM THANH THIEN | Testing implemented functions of website | Improve website's interface
TA XUAN HOANG SON |  | Complete screencast documentation
HA THANH DUNG | Create Term and Condition interface
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website |  |  | 26/4/2019
PHAM THANH THIEN | Create scrum documentation
TA XUAN HOANG SON
HA THANH DUNG | Create Block upload feature | Improve website's interface
DUONG HOANG ANH TUAN
TRAN PHUOC DAT
NGUYEN VIET NGUYEN | Testing implemented functions of website, create scrum documentation |  |  | 27/4/2019
PHAM THANH THIEN | Design student registration interface | Improve website's interface
TA XUAN HOANG SON
HA THANH DUNG | Create student registration function | Improve website's interface
DUONG HOANG ANH TUAN
TRAN PHUOC DAT