## Sprint Backlog
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | 29/04/2019
| UNIVERSITY MAGAZINE MANAGEMENT | NGUYEN VIET NGUYEN | 25/03/2019 | 29/04/2019 |  | 73.7% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | NGUYEN VIET NGUYEN |  | 25/03/2019 | 31/03/2019 | 7 | Inprogress
| Users Requirements |  | NGUYEN VIET NGUYEN |  | 25/03/2019 | 25/03/2019 | 1 | Complete
| Requirement Specification |  | TA XUAN HOANG SON |  | 25/03/2019 | 25/03/2019 | 1 | Complete
| Sitemap |  | TRAN PHUOC DAT |  | 27/03/2019 | 27/03/2019 | 1 | Inprogress
| Website interface design |  | HA THANH DUNG |  | 30/03/2019 | 30/03/2019 | 1 | Inprogress
| Wire frame |  | DUONG HOANG ANH TUAN |  | 26/03/2019 | 26/03/2019 | 1 | Inprogress
| Sprint 2 |  | NGUYEN VIET NGUYEN |  | 2019-01-04 | 2019-07-04 | 7 | Complete
| login function |  | HA THANH DUNG |  | 2019-02-04 | 2019-02-04 | 1 | Complete
| Upload function |  | HA THANH DUNG |  | 2019-04-04 | 2019-04-04 | 1 | Complete
| Send mail function |  | HA THANH DUNG |  | 2019-05-04 | 2019-05-04 | 1 | Complete
| Sitemap |  | TRAN PHUOC DAT |  | 2019-06-04 | 2019-06-04 | 1 | Complete
| Wire frame |  | DUONG HOANG ANH TUAN |  | 2019-06-04 | 2019-06-04 | 1 | Complete
| Sprint 3 |  | NGUYEN VIET NGUYEN |  | 2019-08-04 | 14/4/19 | 6 | Inprogress
| Implement website interface |  | HA THANH DUNG |  | 2019-08-04 | 2019-08-04 | 1 | Inprogress
| Design functionalities for Marketing Coordinator |  | PHAM THANH THIEN |  | 2019-09-04 | 2019-09-04 | 1 | Complete
| Implemment functionalities for Marketing Coordinator |  | HA THANH DUNG |  | 2019-09-04 | 2019-09-04 | 1 | Complete
| Design functionalities for University Marketing Manager |  | PHAM THANH THIEN |  | 2019-10-04 | 2019-10-04 | 1 | Complete
| Implemment functionalities for University Marketing Manager |  | HA THANH DUNG |  | 2019-10-04 | 2019-10-04 | 1 | Complete
| Design functionalities for Guest |  | PHAM THANH THIEN |  | 2019-11-04 | 2019-11-04 | 1 | Complete
| Implemment functionalities for Guest |  | HA THANH DUNG |  | 2019-11-04 | 2019-11-04 | 1 | Complete
| Design functionalities for Student |  | PHAM THANH THIEN |  | 2019-12-04 | 2019-12-04 | 1 | Complete
| Implemment functionalities for Student |  | HA THANH DUNG |  | 2019-12-04 | 2019-12-04 | 1 | Complete
| Sprint 4 |  | NGUYEN VIET NGUYEN |  | 15/4/19 | 21/4/19 | 6 | Complete
| Implement website interface |  | HA THANH DUNG |  | 15/4/19 | 15/4/19 | 1 | Complete
| Design download function |  | HA THANH DUNG |  | 15/4/19 | 15/4/19 | 1 | Complete
| Implement Download function |  | HA THANH DUNG |  | 15/4/19 | 15/4/19 | 1 | Complete
| Design Data Management feature |  | PHAM THANH THIEN |  | 16/4/19 | 16/4/19 | 1 | Complete
| Implemment Date Management feature |  | HA THANH DUNG |  | 16/4/19 | 16/4/19 | 1 | Complete
| Design view only interface |  | NGUYEN VIET NGUYEN |  | 17/4/19 | 17/4/19 | 1 | Complete
| Implement view only interface |  | HA THANH DUNG |  | 17/4/19 | 17/4/19 | 1 | Complete
| Design term and condition section |  | NGUYEN VIET NGUYEN |  | 18/4/19 | 18/4/19 | 1 | Complete
| Implement term and condition section |  | HA THANH DUNG |  | 18/4/19 | 18/4/19 | 1 | Complete
| Design block upload feature |  | HA THANH DUNG |  | 19/4/19 | 19/4/19 | 1 | Complete
| Implemment block upload feature |  | HA THANH DUNG |  | 19/4/19 | 19/4/19 | 1 | Complete
| Design registion feature |  | PHAM THANH THIEN |  | 20/4/19 | 20/4/19 | 1 | Complete
| Implemment registion feature |  | HA THANH DUNG |  | 20/4/19 | 20/4/19 | 1 | Complete
| Sprint 5 |  | NGUYEN VIET NGUYEN |  | 22/4/19 | 29/4/19 | 7 | Inprogress
| Data data encryption feature |  | PHAM THANH THIEN |  | 22/4/19 | 22/4/19 | 1 | Complete
| Implement data encryption feature |  | HA THANH DUNG |  | 22/4/19 | 22/4/19 | 1 | Complete
| Design notification system |  | PHAM THANH THIEN |  | 23/4/19 | 23/4/19 | 1 | Complete
| Implemment notification system |  | HA THANH DUNG |  | 23/4/19 | 23/4/19 | 1 | Complete
| Design validation system |  | HA THANH DUNG |  | 24/4/19 | 24/4/19 | 1 | Complete
| Implemment validation system |  | NGUYEN VIET NGUYEN |  | 24/4/19 | 24/4/19 | 1 | Complete
| Improve website interface |  | HA THANH DUNG |  | 25/4/19 | 27/4/19 | 3 | Inprogress
| Implement website interface |  | HA THANH DUNG |  | 2022-09-25 | 2022-09-29 | 4 | Complete